TRIBHUVAN UNIVERSITY
INSTITUTE OF SCIENCE AND TECHNOLOGY

Final Year Project Report on

ScaffoldPM

AI-Driven Project Planning and Optimization System

For the partial fulfillment of the requirements of the degree of

Bachelor of Science in Computer Science and Information Technology (B.Sc.CSIT)

awarded by Tribhuvan University

Submitted By:

[Student Name 1] ([Roll Number])
[Student Name 2] ([Roll Number])

ST. XAVIER'S COLLEGE

Maitighar, Kathmandu, Nepal

Submitted To:

Office of the Dean
Institute of Science and Technology
Tribhuvan University, Kathmandu

June 2026

# SUPERVISOR RECOMMENDATION

This is to certify that the final year project entitled "ScaffoldPM: AI-Driven Project Planning and Optimization System" is an academic work completed by [Student Name 1] and [Student Name 2] under my supervision. The project has been prepared for the partial fulfillment of the requirements for the degree of Bachelor of Science in Computer Science and Information Technology.

The information presented in this project report has not been submitted earlier to the best of my knowledge. I recommend this report for evaluation.

Signature of the Supervisor
Name: [Supervisor Name]
Designation: [Designation]
Date: June 2026

# CERTIFICATE OF APPROVAL

The undersigned certify that they have read and recommended to the Department of Computer Science, St. Xavier's College for acceptance, a final year project report entitled "ScaffoldPM: AI-Driven Project Planning and Optimization System" submitted by [Student Name 1] and [Student Name 2] in partial fulfillment of the requirements for the degree of Bachelor of Science in Computer Science and Information Technology.

.................................
Project Supervisor

.................................
Internal Examiner

.................................
Head of Department

.................................
External Examiner

# ACKNOWLEDGEMENT

We would like to express our sincere gratitude to the Department of Computer Science, St. Xavier's College, Maitighar, Kathmandu, for providing us with the opportunity to undertake this final year project.

We are deeply thankful to our respected supervisor for continuous guidance, suggestions, and encouragement throughout the development of ScaffoldPM. The feedback received during planning, implementation, and documentation helped us improve both the technical quality and academic presentation of the project.

We also extend our thanks to the faculty members, friends, and all individuals who directly or indirectly supported us during the completion of this work.

[Student Name 1]
[Student Name 2]

# ABSTRACT

ScaffoldPM is an AI-driven project planning and optimization system designed to automate the generation of structured project plans from unstructured scope documents. The system accepts a project scope document and basic project metadata, extracts readable text, and uses a large language model to generate a work breakdown structure containing phases, activities, tasks, required skills, and dependencies.

After generating the WBS, ScaffoldPM assigns tasks to suitable team members using semantic skill matching, estimates task duration using an XGBoost-based machine learning model or fallback heuristic logic, schedules tasks according to dependencies and team availability, and identifies critical tasks through critical path analysis. The backend is implemented using FastAPI, Pydantic, SQLAlchemy, SQLite, LangChain, OpenAI API, Sentence Transformers, XGBoost, and NetworkX.

The project demonstrates how artificial intelligence, natural language processing, machine learning, and project management principles can be combined to reduce manual planning effort and improve project organization.

Keywords: Artificial Intelligence, Project Management, Work Breakdown Structure, Critical Path Method, FastAPI, XGBoost, Sentence Transformers.

# TABLE OF CONTENTS

SUPERVISOR RECOMMENDATION

CERTIFICATE OF APPROVAL

ACKNOWLEDGEMENT

ABSTRACT

LIST OF ABBREVIATIONS

LIST OF FIGURES

LIST OF TABLES

CHAPTER 1 - INTRODUCTION

CHAPTER 2 - BACKGROUND STUDY AND LITERATURE REVIEW

CHAPTER 3 - SYSTEM ANALYSIS

CHAPTER 4 - SYSTEM DESIGN

REFERENCES

# LIST OF ABBREVIATIONS

| Abbreviation | Full Form |
| --- | --- |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| CPM | Critical Path Method |
| CRUD | Create, Read, Update, Delete |
| DFD | Data Flow Diagram |
| ERD | Entity Relationship Diagram |
| LLM | Large Language Model |
| ML | Machine Learning |
| NLP | Natural Language Processing |
| ORM | Object Relational Mapping |
| WBS | Work Breakdown Structure |

# LIST OF FIGURES

Figure 1: Use Case Diagram for ScaffoldPM

Figure 2: Gantt Chart for ScaffoldPM Development

Figure 3: Class Diagram for ScaffoldPM

Figure 4: Sequence Diagram for Project Plan Generation

Figure 5: Activity Diagram for AI-Assisted Project Planning Pipeline

Figure 6: State Diagram for Project Generation Request Lifecycle

Figure 7: Component Diagram for ScaffoldPM

Figure 8: Deployment Diagram for ScaffoldPM

Figure 9: Frontend Interface Design for ScaffoldPM

# LIST OF TABLES

Table 1: Functional Requirements of ScaffoldPM

Table 2: Non-Functional Requirements of ScaffoldPM

Table 3: Hardware Requirements

Table 4: Software Requirements

Table 5: Entity to Relation Mapping

# CHAPTER 1 - INTRODUCTION

## Introduction

Project planning is one of the most important activities in software engineering and information system development. Before a project can be implemented successfully, the project manager must understand the scope, divide the work into smaller components, estimate the time required for each task, assign suitable team members, and identify activities that can delay the whole project. According to the PMBOK Guide, project management involves coordinated planning and control of scope, schedule, resources, and related activities [1].

In many organizations, the initial planning process is still performed manually. The project manager reads a requirement document, prepares phases and tasks, estimates duration, and assigns work based on personal judgment. This process consumes time and can introduce human error, especially when the requirement document is long or unclear. Inaccurate software effort estimation is a known challenge because wrong estimates can affect cost, schedule, and delivery reliability [8].

ScaffoldPM is proposed as an AI-driven project planning and optimization system that assists project managers in converting an uploaded scope document into a structured project plan. It extracts text from PDF, DOC/DOCX, or TXT documents, generates a work breakdown structure using a large language model, assigns tasks using semantic skill matching, estimates duration using a machine learning model or heuristic fallback, schedules tasks, identifies critical path tasks, and stores the final plan in a database.

## Problem Statement

Traditional project planning requires a project manager to manually read the scope document and identify phases, activities, tasks, dependencies, required skills, and schedules. This process is repetitive and depends heavily on the experience of the project manager. Important tasks may be missed, dependencies may be assigned incorrectly, and duration estimates may become inconsistent.

Another major issue is task assignment. When team members have different roles, skills, and experience levels, assigning work manually can lead to imbalance. Some members may receive too many tasks while other suitable members remain underused. Similarly, without proper dependency analysis, project managers may fail to identify critical tasks that directly affect the project deadline.

Therefore, there is a need for a system that can automatically generate a structured project plan from a scope document and support project managers with task assignment, effort estimation, scheduling, and critical path analysis.

## Objectives

The main objective of this project is to design and implement an AI-driven backend system that generates and optimizes project plans from uploaded scope documents.

To extract readable text from uploaded PDF, DOC/DOCX, and TXT project scope documents.

To generate a detailed work breakdown structure containing phases, activities, and tasks.

To identify task types, required skills, and task dependencies.

To assign tasks to team members based on semantic similarity, skill match, experience, and workload.

To estimate task duration using an XGBoost model or heuristic fallback logic.

To schedule tasks according to dependencies, working days, and team member availability.

To calculate slack and identify critical path tasks.

To store generated project plans in a relational database and expose them through REST APIs.

## Scope and Limitations

### Scope

The project focuses on the backend implementation of an AI-assisted project planning system. The major scope of ScaffoldPM includes the following:

Uploading and processing project scope documents.

Extracting and cleaning text from PDF, DOC/DOCX, and TXT files.

Generating WBS data through an LLM-powered module.

Managing projects, phases, activities, tasks, and team members.

Assigning tasks using semantic embeddings and workload balancing.

Estimating task duration through a trained model or heuristic logic.

Scheduling tasks while skipping weekends.

Analyzing task dependencies using critical path method.

Persisting project data in SQLite through SQLAlchemy ORM.

Providing API endpoints for project generation, retrieval, task status update, and reassignment.

### Limitations

The quality of the generated WBS depends on the quality of the uploaded scope document and the LLM response.

The current implementation requires an OpenAI API key for WBS generation.

The frontend directory exists but a complete production frontend is not implemented in the current repository.

The scheduler uses a greedy approach and may not always produce the globally optimal schedule.

The system excludes weekends but does not currently consider public holidays, leave days, or part-time availability.

Authentication, authorization, and role-based access control are not implemented.

Skills and dependencies are stored as comma-separated text rather than fully normalized relational tables.

## Development Methodology

An iterative and incremental development methodology was followed for ScaffoldPM. The project was divided into independent modules such as document extraction, WBS generation, task matching, duration prediction, scheduling, critical path analysis, and database persistence. Each module was implemented and tested separately before being integrated into the main API workflow.

This approach was suitable because the project combines multiple technologies and algorithms. Building the system incrementally allowed the document extraction module to be validated first, followed by WBS generation, task assignment, duration estimation, scheduling, and database operations. The modular design also supports future extension such as frontend integration, authentication, deployment, and improved optimization.

## Report Organization

The report is organized into the following chapters:

Chapter 1 introduces the project, problem statement, objectives, scope, limitations, development methodology, and report organization.

Chapter 2 presents the background study and literature review related to project planning, WBS, CPM, effort estimation, embeddings, and technologies used.

Chapter 3 describes system analysis, requirements, feasibility analysis, and object-oriented analysis models.

Chapter 4 explains the system design, including architecture, database design, interface design, and algorithm descriptions.

# CHAPTER 2 - BACKGROUND STUDY AND LITERATURE REVIEW

## Background Study

Project planning involves defining the work required to complete a project and organizing it into manageable components. A Work Breakdown Structure is widely used to decompose project scope into smaller deliverables and work packages [2]. In software projects, this decomposition is useful because it allows project teams to understand the required work, estimate effort, assign responsibilities, and track progress.

Critical Path Method is another important project management technique. It represents project activities and their dependencies and identifies the sequence of tasks that controls the total project duration [4]. Tasks on the critical path have zero slack, meaning any delay in those tasks can delay the entire project. ScaffoldPM uses this idea to mark tasks that require special attention from the project manager.

Software effort estimation is a difficult problem because development effort depends on task complexity, developer experience, technology stack, requirement clarity, and many other factors. Traditional approaches such as COCOMO provided early structured models for effort estimation [7]. More recent studies have explored machine learning techniques for improving software effort estimation accuracy when historical project data is available [9].

Natural language processing and large language models provide new opportunities for transforming unstructured requirement documents into structured outputs. ScaffoldPM uses an LLM to generate phases, activities, tasks, required skills, and dependencies from scope text. It also uses semantic sentence embeddings for matching tasks with team members. Sentence-BERT shows that sentence embeddings can represent sentence meaning in a way that supports semantic similarity comparison [5].

## Literature Review

| Source | Main Contribution | Use in ScaffoldPM |
| --- | --- | --- |
| Project Management Institute (2021) | Provides general project management principles including planning, scope, schedule, and resource coordination. | Supports the overall project management foundation of ScaffoldPM. |
| Project Management Institute (2019) | Explains WBS as a structured decomposition of project scope into manageable work components. | Supports the WBS-based phase, activity, and task structure. |
| Hans (2013) | Discusses WBS as a tool for software project scope verification. | Justifies using WBS in software project planning. |
| Kelley and Walker (1959) | Introduces critical-path planning and scheduling. | Supports dependency analysis and critical task identification. |
| Boehm (1981) | Presents foundational work in software engineering economics and effort estimation. | Supports the need for systematic software effort estimation. |
| Reimers and Gurevych (2019) | Introduces Sentence-BERT for semantically meaningful sentence embeddings. | Supports semantic task-team matching. |
| Chen and Guestrin (2016) | Introduces XGBoost as a scalable tree boosting system. | Supports the task duration prediction model. |

## Existing System

Many project management tools provide task boards, Gantt charts, calendars, and collaboration features. However, these systems often require the project manager to manually create tasks, estimate durations, define dependencies, and assign team members. The planning output depends on the user's ability to interpret requirements and convert them into a structured plan.

Existing manual systems also have limited intelligence in matching tasks to team members. A manager may know the team personally, but in larger teams or unfamiliar projects, it becomes difficult to maintain fair workload distribution and skill-based assignment. Similarly, traditional systems may show schedules but do not automatically generate the plan from the original scope document.

## Proposed System

ScaffoldPM proposes an AI-assisted backend system that reduces manual effort by converting the uploaded scope document into a structured, scheduled, and stored project plan. The proposed system integrates the following components:

Document extraction for reading PDF, DOC/DOCX, and TXT documents.

LLM-based WBS generation for producing phases, activities, tasks, dependencies, and required skills.

Semantic task assignment using SentenceTransformer embeddings.

Duration estimation using XGBoost model or heuristic fallback.

Dependency-aware scheduling using working-day calculations.

Critical path analysis using directed graph processing.

Database persistence and REST APIs for project management operations.

## Technology Review

| Technology | Description | Role in System |
| --- | --- | --- |
| FastAPI | Python web framework used to build REST APIs with automatic documentation [10]. | API layer |
| Pydantic | Data validation and schema definition library [11]. | Request/response validation |
| SQLAlchemy | ORM used for database models and asynchronous operations [12]. | Database layer |
| SQLite | Lightweight serverless database [13]. | Local persistence |
| LangChain | Framework for connecting application logic with LLMs [14]. | WBS generation workflow |
| OpenAI API | LLM text generation and structured output support [15], [16]. | AI-generated WBS |
| Sentence Transformers | Library for sentence embeddings and semantic similarity [17]. | Task-member matching |
| XGBoost | Gradient boosting library for supervised learning [18]. | Duration prediction |
| NetworkX | Graph processing library with DAG utilities [19]. | Critical path analysis |

# CHAPTER 3 - SYSTEM ANALYSIS

## System Analysis

System analysis identifies the requirements, feasibility, users, processes, and data flow of the proposed system. ScaffoldPM is analyzed as a backend-centered project planning system that receives an uploaded document and project metadata, processes them through AI and scheduling modules, stores the result, and provides APIs for later retrieval and management.

The primary actor of the system is the project manager or team lead. The user uploads a scope document, provides project dates and team member details, and receives a generated project plan. The generated plan contains tasks, assignments, estimated hours, schedules, and critical path information.

## Requirement Analysis

### Functional Requirements

| ID | Requirement |
| --- | --- |
| FR1 | The system shall allow the user to upload a project scope document. |
| FR2 | The system shall extract text from PDF, DOC/DOCX, and TXT documents. |
| FR3 | The system shall accept project name, start date, end date, and team member details. |
| FR4 | The system shall generate a WBS containing phases, activities, and tasks. |
| FR5 | The system shall identify task types, required skills, and dependencies. |
| FR6 | The system shall assign tasks to suitable team members. |
| FR7 | The system shall estimate task duration in hours. |
| FR8 | The system shall schedule tasks based on dependencies and availability. |
| FR9 | The system shall identify critical path tasks and slack values. |
| FR10 | The system shall save generated project plans in the database. |
| FR11 | The system shall list saved projects and fetch a project by ID. |
| FR12 | The system shall update task status and task assignment. |

### Non-Functional Requirements

| ID | Requirement |
| --- | --- |
| NFR1 | The system should validate incoming data using defined schemas. |
| NFR2 | The system should provide structured JSON API responses. |
| NFR3 | The system should handle invalid documents and malformed payloads gracefully. |
| NFR4 | The backend should use modular architecture for maintainability. |
| NFR5 | The database operations should be asynchronous where possible. |
| NFR6 | The system should use fallback duration estimation if the ML model is unavailable. |
| NFR7 | The system should be extensible for future frontend, authentication, and deployment. |

## Use Case Analysis

The main use cases of ScaffoldPM are performed by the project manager. The project manager can generate a WBS, view stored projects, update task status, and reassign tasks.

Figure 1: Use Case Diagram for ScaffoldPM Image placeholder description: Create a UML use case diagram with one actor named Project Manager. Connect the actor to these use cases: Upload Scope Document, Enter Project Details, Generate WBS, View Project Plan, View Critical Path, List Saved Projects, Update Task Status, and Reassign Task. The system boundary should be labelled ScaffoldPM.

Figure 1: Use Case Diagram for ScaffoldPM

## Feasibility Analysis

### Technical Feasibility Analysis

The project is technically feasible because the required technologies are available as open-source or API-based tools. FastAPI, SQLAlchemy, SQLite, Sentence Transformers, XGBoost, NetworkX, pdfplumber, PyMuPDF, and python-docx support the main backend operations. The WBS generation module depends on OpenAI API access through LangChain.

### Hardware Requirements

| Component | Minimum Requirement |
| --- | --- |
| Processor | Intel Core i5 or equivalent |
| RAM | 8 GB minimum, 16 GB recommended |
| Storage | 2 GB free storage for source code, dependencies, dataset, and database |
| Network | Internet connection required for OpenAI API and model dependency download |

### Software Requirements

| Software | Purpose |
| --- | --- |
| Python | Backend programming language |
| FastAPI and Uvicorn | API development and local server execution |
| SQLite | Local relational database |
| OpenAI API Key | LLM-based WBS generation |
| Python libraries from requirements.txt | Document extraction, validation, ML, NLP, scheduling, and graph analysis |
| API testing tool | Testing endpoints through Swagger UI or Postman |

### Operational Feasibility

The system is operationally feasible because project managers already work with scope documents, project dates, teams, and tasks. ScaffoldPM fits into this workflow by reducing the manual effort required to prepare the initial plan. The generated plan can later be reviewed and modified by the manager.

### Economic Feasibility

The system uses mainly open-source technologies, which reduces development cost. The main recurring cost is the LLM API usage required for WBS generation. For academic and prototype use, the system can run locally with SQLite and does not require paid database or hosting services.

### Schedule Feasibility

The modular nature of the system makes it suitable for incremental development within a final year project schedule. Core modules can be implemented and tested independently, and future features such as frontend visualization and authentication can be added later.

Figure 2: Gantt Chart for ScaffoldPM Development Image placeholder description: Create a Gantt chart showing project phases across weeks: Requirement Study, Literature Review, Backend Setup, Document Extraction, WBS Generation, Task Matching, Duration Prediction, Scheduling and CPM, Database Integration, API Testing, Documentation, and Final Review.

Figure 2: Gantt Chart for ScaffoldPM Development

## Object-Oriented Analysis

Object-Oriented Analysis (OOA) is used to model ScaffoldPM through UML-based conceptual diagrams. It helps describe the static structure of the system, the interaction between system components, the internal workflow of project plan generation, and the lifecycle of a generated planning request. Since ScaffoldPM is designed as a modular backend system, OOA is useful for understanding how entities such as Project, Phase, Activity, Task, TeamMember, and WBSResponse interact with service modules such as DocumentExtractor, WBSGenerator, TaskMatcher, DurationPredictor, Scheduler, CPMAnalyzer, and ProjectRepository.

The object-oriented view of ScaffoldPM focuses on four major UML diagrams: class diagram, sequence diagram, activity diagram, and state diagram. The class diagram shows the static structure of the system. The sequence diagram explains how a project generation request flows through different components. The activity diagram presents the complete AI-assisted project planning pipeline. The state diagram shows the lifecycle of a project generation request from upload to completion or failure.

### Class Diagram

The class diagram identifies the core classes, data models, services, and relationships used in ScaffoldPM. The Project class represents the main project plan and contains project metadata such as project name, description, start date, end date, total working days, and created date. A Project contains one or more Phase objects, and each Phase contains one or more Activity objects. Each Activity contains multiple Task objects. The Task class stores task-specific information such as title, description, task type, status, estimated hours, start date, end date, dependencies, required skills, assigned member, slack, and critical path flag.

The TeamMember class represents members available for the project. Each team member has an id, name, role, skills, and experience level. Tasks can be assigned to team members based on semantic skill matching. The WBSResponse class represents the generated project plan returned by the system, including the project object, optional summary, and total duration in working days.

The service classes represent the main processing modules of ScaffoldPM. DocumentExtractor extracts and cleans text from uploaded documents. WBSGenerator uses the extracted scope text and project metadata to generate phases, activities, and tasks. TaskMatcher assigns tasks to suitable team members. DurationPredictor estimates the effort required for each task. Scheduler assigns start and end dates based on dependencies and member availability. CPMAnalyzer calculates slack and identifies critical tasks. ProjectRepository handles database operations such as saving, fetching, listing, and updating project data.

Figure 3: Class Diagram for ScaffoldPM

[Insert figure 3: class diagram for scaffoldpm here. Suggested image description: Create a UML class diagram showing Project, Phase, Activity, Task, TeamMember, WBSResponse, DocumentExtractor, WBSGenerator, TaskMatcher, DurationPredictor, Scheduler, CPMAnalyzer, and ProjectRepository. Show Project-to-Phase, Phase-to-Activity, Activity-to-Task, TeamMember-to-Task, Project-to-TeamMember, Task self-dependency, and service dependency relationships.]

### Sequence Diagram: Project Plan Generation

The sequence diagram describes the interaction between the user and ScaffoldPM components during project plan generation. The process begins when the Project Manager uploads a scope document and submits project metadata such as project name, dates, and team member details. The frontend or API client sends a multipart request to the FastAPI backend.

The ProjectRouter validates the payload and forwards the uploaded file to the DocumentExtractor. The DocumentExtractor extracts and cleans the text from the scope document. The cleaned scope text is passed to the WBSGenerator, which uses the LLM service to generate a structured work breakdown structure. After the WBS is generated, the TaskMatcher assigns tasks to suitable team members using semantic similarity. The DurationPredictor estimates task effort, the Scheduler calculates task start and end dates, and the CPMAnalyzer identifies critical tasks. Finally, the ProjectRepository stores the generated project plan in the database and the API returns the complete project plan to the user.

Participants: Project Manager, Frontend/API Client, FastAPI App, ProjectRouter, DocumentExtractor, WBSGenerator, OpenAI LLM Service, TaskMatcher, DurationPredictor, Scheduler, CPMAnalyzer, ProjectRepository, SQLite Database.

Figure 4: Sequence Diagram for Project Plan Generation

[Insert figure 4: sequence diagram for project plan generation here. Suggested image description: Create a UML sequence diagram with lifelines for Project Manager, Frontend/API Client, FastAPI App, ProjectRouter, DocumentExtractor, WBSGenerator, OpenAI LLM Service, TaskMatcher, DurationPredictor, Scheduler, CPMAnalyzer, ProjectRepository, and SQLite Database. Show the POST /api/project/generate-wbs flow from upload to saved project response, including validation and common error responses.]

### Activity Diagram: AI-Assisted Project Planning Pipeline

The activity diagram represents the complete workflow followed by ScaffoldPM during project plan generation. The process starts when the user uploads a scope document and submits the project payload. The system validates the request and checks whether the uploaded document type is supported. If the request is invalid or the file type is unsupported, the system returns an error response.

If the input is valid, the document text is extracted and cleaned. The cleaned text is used by the WBS generation module to produce phases, activities, tasks, required skills, and dependencies. The system then resolves dependencies, assigns tasks to team members, estimates duration, schedules tasks, analyzes the critical path, stores the project, and returns the generated plan. This activity flow shows the internal decision points and processing stages of ScaffoldPM.

Figure 5: Activity Diagram for AI-Assisted Project Planning Pipeline

[Insert figure 5: activity diagram for ai-assisted project planning pipeline here. Suggested image description: Create a UML activity diagram showing request validation, file type checking, document extraction, text cleaning, LLM-based WBS generation, dependency resolution, semantic task assignment, duration estimation with ML-or-heuristic decision, scheduling, critical path analysis, database saving, success response, and error paths.]

### State Diagram: Project Generation Request Lifecycle

The state diagram shows the lifecycle of a project generation request in ScaffoldPM. A request begins in the idle state before the user uploads a document and submits project details. After submission, the request moves to validation. If validation fails, the request enters an error state. If validation succeeds, the request moves through document extraction, WBS generation, task assignment, duration estimation, scheduling, critical path analysis, and database persistence.

When all processing steps complete successfully, the request enters the completed state and the generated project plan is returned to the user. If an error occurs during extraction, WBS generation, database saving, or any major processing step, the request moves to a failed state with an appropriate HTTP error response. This state model helps describe how ScaffoldPM handles both successful and unsuccessful project generation workflows.

Figure 6: State Diagram for Project Generation Request Lifecycle

[Insert figure 6: state diagram for project generation request lifecycle here. Suggested image description: Create a UML state diagram with states Idle, Submitted, Validating Request, Invalid Request, Extracting Document Text, Generating WBS, Resolving Dependencies, Assigning Tasks, Estimating Durations, Scheduling Tasks, Analyzing Critical Path, Saving Project, Completed, and Failed. Include transitions for success and HTTP error cases.]

# CHAPTER 4 - SYSTEM DESIGN

This chapter presents the detailed design of ScaffoldPM, refining the analysis models into implementation-ready specifications for an AI-driven project planning backend. The design addresses the complete workflow from scope document upload through document extraction, LLM-based WBS generation, semantic task assignment, duration estimation, dependency-aware scheduling, critical path analysis, database persistence, and JSON response delivery.

## Architectural Design

ScaffoldPM follows a modular service-layer architecture with a clear separation between the API layer, processing modules, and database layer. The backend is implemented using FastAPI and exposes REST endpoints for project generation, project retrieval, task status update, and task reassignment.

API Layer: Handles HTTP routing, multipart file upload, payload validation, error handling, and JSON response construction. The project.py router defines the main /api/project endpoints, while health.py provides backend health and extraction testing endpoints.

Service Layer: Contains the main processing modules. The document extractor reads PDF, DOC/DOCX, and TXT files; the WBS generator creates project structure using an LLM; the matcher assigns tasks using semantic embeddings; the predictor estimates duration; the scheduler assigns dates; and the CPM analyzer identifies critical tasks.

Data Layer: Contains Pydantic schemas and SQLAlchemy models. Pydantic models validate and serialize project objects, while SQLAlchemy models define database tables for projects, phases, activities, tasks, team members, and project-member relationships.

Infrastructure Layer: Provides configuration, OpenAI API connectivity, asynchronous SQLite access, model loading for duration prediction, SentenceTransformer embedding support, document parsing libraries, and NetworkX graph processing.

### Component Diagram

The component diagram describes the major software components of ScaffoldPM and how they interact during project generation.

Client Tier: A future web frontend or API testing client that uploads the scope document and sends project metadata to the backend.

API Tier: FastAPI application server running the ScaffoldPM backend. It exposes routes under /api and /api/project and provides OpenAPI documentation through FastAPI.

Processing Tier: DocumentExtractor, WBSGenerator, TaskMatcher, DurationPredictor, Scheduler, and CPMAnalyzer modules.

External AI Service: OpenAI LLM service used by the WBS generation module through LangChain.

Persistence Tier: SQLAlchemy asynchronous database access layer and SQLite database file.

Interfaces: ProjectRouter communicates with DocumentExtractor, WBSGenerator, TaskMatcher, DurationPredictor, Scheduler, CPMAnalyzer, and ProjectRepository. WBSGenerator communicates with OpenAI API. ProjectRepository communicates with SQLite.

Figure 7: Component Diagram for ScaffoldPM

[Insert figure 7: component diagram for scaffoldpm here. Suggested image description: Create a UML component diagram with Client/API Client, FastAPI App, ProjectRouter, DocumentExtractor, WBSGenerator, OpenAI LLM Service, TaskMatcher, DurationPredictor, Scheduler, CPMAnalyzer, ProjectRepository, SQLAlchemy ORM, and SQLite Database. Show REST call from client to API, service calls between router and modules, external call to OpenAI, and persistence call to SQLite.]

### Deployment Diagram

The deployment design explains how ScaffoldPM can be hosted in a practical environment. The current implementation can run locally for academic demonstration, but the design also supports future deployment to a server environment.

Node 1 - Client Device: Laptop or desktop browser, Swagger UI, Postman, or a future frontend application. Communicates with the backend through HTTP requests.

Node 2 - API Server: Python runtime running FastAPI with Uvicorn ASGI server. Recommended configuration is Python 3.12 or compatible version, 4 vCPU, 8 GB RAM, and SSD storage.

Node 3 - AI/ML Runtime: Executes SentenceTransformer embeddings, XGBoost duration prediction, and document processing libraries. The LLM call is sent to the external OpenAI API over the internet.

Node 4 - Database Storage: SQLite database file scaffoldpm.db for local persistence. In production, this can be replaced with PostgreSQL or another managed relational database.

Communication: Client communicates with FastAPI over HTTP/HTTPS; FastAPI communicates with OpenAI API over HTTPS; FastAPI accesses the SQLite database through SQLAlchemy and aiosqlite.

Figure 8: Deployment Diagram for ScaffoldPM

[Insert figure 8: deployment diagram for scaffoldpm here. Suggested image description: Create a UML deployment diagram with Client Device, API Server running FastAPI/Uvicorn, AI/ML Runtime modules, External OpenAI API, and SQLite Database Storage. Show HTTP/HTTPS communication, local module execution, and database access.]

## Data Model Design

The data model design stores the generated project plan in a relational structure. A project contains phases, phases contain activities, and activities contain tasks. Team members are linked to projects through a junction table and can be assigned to tasks. The schema is suitable for storing WBS hierarchy, schedule information, assignment information, and critical path results.

| Table | Column | Type | Constraints / Description |
| --- | --- | --- | --- |
| projects | id, name | String | Primary key; project name is required |
| projects | description, summary | Text | Optional project and AI summary fields |
| projects | start_date, end_date, created_at | Date/DateTime | Stores project timeline and creation date |
| projects | total_working_days, total_duration_days | Integer | Stores planned and computed working duration |
| team_members | id, name, role | String | Primary key; name and role are required |
| team_members | skills, experience | Text/String | Skills stored as comma-separated text; experience defaults to mid |
| project_members | project_id, team_member_id | String | Composite primary key; junction table |
| phases | id, project_id, title, order | String/Integer | Phase belongs to project and has display order |
| activities | id, phase_id, title | String | Activity belongs to phase |
| tasks | id, activity_id, assigned_to, title | String | Task belongs to activity and may be assigned to a team member |
| tasks | task_type, status | Enum | Task category and Kanban status |
| tasks | estimated_hours, start_date, end_date | Float/Date | Effort estimate and scheduled dates |
| tasks | dependencies, skills_required | Text | Comma-separated task IDs and required skills |
| tasks | is_critical, slack | Boolean/Float | Critical path result fields |

### Normalization

First Normal Form (1NF): Main entities are separated into projects, phases, activities, tasks, and team members. Most attributes are atomic; however, skills and dependencies are currently stored as comma-separated text for implementation simplicity.

Second Normal Form (2NF): Non-key attributes depend on the full primary key. Junction table project_members uses project_id and team_member_id to represent many-to-many membership without repeating team data inside project rows.

Third Normal Form (3NF): Project details, phase details, activity details, task details, and team member details are stored in separate tables to reduce transitive dependency. Future versions can further normalize skills, task dependencies, and required skills into separate relation tables.

## API Interface Design

The ScaffoldPM backend exposes RESTful APIs using FastAPI. The main API accepts multipart form data containing the uploaded document and JSON payload, then returns a structured project plan.

| Endpoint | Method | Input | Output / Purpose |
| --- | --- | --- | --- |
| /api/health | GET | None | Returns backend status, application name, and debug mode |
| /api/health/extract | POST | Uploaded file | Returns extracted document text for testing |
| /api/project/generate-wbs | POST | file UploadFile; payload JSON string | Generates WBS, assignments, schedule, total duration, and critical path |
| /api/project/ | GET | None | Lists saved project summaries |
| /api/project/{project_id} | GET | project_id path parameter | Returns full saved project with phases, activities, tasks, and team |
| /api/project/task/status | PATCH | task_id, new_status | Updates task status to todo, in_progress, or done |
| /api/project/task/assign | PATCH | task_id, member_id | Reassigns a task to another team member |

| Field | Type | Required | Description |
| --- | --- | --- | --- |
| project_name | string | Yes | Name of the project to be planned |
| start_date | date | Yes | Project start date |
| end_date | date | Yes | Project end date |
| team_members | list | Yes | List of team members with id, name, role, skills, and experience |
| file | UploadFile | Yes | Scope document in PDF, DOC, DOCX, or TXT format |

## Frontend Interface Design

The current repository contains the backend implementation and an empty frontend directory. The frontend interface design is therefore proposed for future integration. It should consume the REST APIs provided by ScaffoldPM and present the generated plan in a user-friendly project management interface.

Navigation: Fixed top navigation with Project List, Generate Project, Team Members, WBS View, Schedule, Critical Path, and Settings links.

Generate Project Page: Form fields for project name, start date, end date, scope document upload, and dynamic team member entry.

WBS Viewer: Tree-style layout showing project, phases, activities, and tasks with expandable/collapsible nodes.

Task Board: Kanban-style columns for todo, in_progress, and done tasks, with assignment and status update controls.

Schedule View: Gantt-style chart showing task start dates, end dates, dependencies, and critical tasks.

Critical Path View: Highlighted list or graph of zero-slack tasks that directly affect project duration.

Figure 9: Frontend Interface Design for ScaffoldPM

[Insert figure 9: frontend interface design for scaffoldpm here. Suggested image description: Create a UI wireframe showing a ScaffoldPM dashboard with sidebar or top navigation, project generation form, document upload field, team member input area, WBS tree panel, task table/Kanban board, schedule view, and critical path summary.]

## Algorithm Details

This section provides detailed algorithms for the core ScaffoldPM processing pipeline, reflecting the backend implementation.

### Document Extraction Algorithm

The document extraction algorithm converts uploaded scope documents into clean text. It supports PDF, DOC/DOCX, and TXT files. For PDF files, pdfplumber is used first, and PyMuPDF is used as a fallback when text extraction fails. DOC/DOCX files are processed using python-docx, while TXT files are decoded using UTF-8 or Latin-1 fallback.

Identify file extension and content type.

Select the appropriate extractor for PDF, DOC/DOCX, or TXT.

Extract page text, paragraph text, or raw text depending on the file type.

Remove repeated headers, repeated footers, page numbers, and extra whitespace.

Return cleaned scope text to the project generation workflow.

### WBS Generation Algorithm

The WBS generation algorithm uses a large language model through LangChain to transform cleaned scope text into a structured project hierarchy. The output is parsed using Pydantic models so that phases, activities, tasks, dependencies, task types, and required skills are returned in a predictable schema.

Prepare project metadata, team member data, project dates, and extracted scope text.

Build a prompt requesting 4 to 6 phases, 3 to 6 activities per phase, and 4 to 8 tasks per activity.

Invoke the LLM and request valid JSON that matches the expected schema.

Parse the LLM output into structured Pydantic objects.

Generate internal UUIDs for project, phases, activities, and tasks.

Resolve dependency names from task titles into internal task IDs.

### Semantic Task Matching Algorithm

The task matching algorithm assigns tasks to team members based on semantic similarity, experience, task complexity, and workload distribution. SentenceTransformer embeddings are generated for task profiles and team member profiles.

Match score = (semantic_similarity * experience_multiplier) / load_penalty.

Create member profile text from role, skills, and experience.

Create task profile text from title, description, task type, and required skills.

Convert profiles into normalized embeddings using all-MiniLM-L6-v2.

Compute similarity between each task and each team member.

Adjust score using experience multiplier and workload penalty.

Assign each task to the member with the highest adjusted score.

### Duration Estimation Algorithm

The duration estimation module first attempts to load a trained XGBoost regression model. If the model file is available, it predicts estimated hours from task features. If the model is unavailable, the system uses fallback heuristic estimation.

| Feature | Description |
| --- | --- |
| task_type | Numeric value representing feature, bugfix, documentation, research, or other |
| description_words | Number of words in task description |
| skills_count | Number of required skills |
| experience_value | Numeric value for junior, mid, or senior assignee |
| hours_estimate | Heuristic base estimate used as a model feature |

Heuristic estimate = base task hours adjusted by experience factor, required skills factor, and description length factor. The value is clamped between 2 and 40 hours and rounded to the nearest 0.5 hour.

### Scheduling and Critical Path Algorithm

The scheduling algorithm assigns start and end dates to tasks using dependencies, working days, and team member availability. Estimated hours are converted into duration days using 8 hours per working day. Weekends are skipped.

Create a task map and dependency map.

Place dependency-free tasks in a ready queue.

Select ready tasks by earliest feasible start date.

Calculate task end date by adding working days.

Update assigned member availability after each scheduled task.

Repeat until all schedulable tasks are assigned dates.

After scheduling, the CPM analyzer builds a directed graph where tasks are nodes and dependencies are edges. It calculates earliest start, earliest finish, latest start, latest finish, and slack. Tasks with zero slack are marked as critical.

### Model Parameters and Configuration

| Parameter | Value | Description |
| --- | --- | --- |
| Backend framework | FastAPI | REST API framework |
| Database | SQLite with aiosqlite | Local relational persistence |
| LLM orchestration | LangChain + OpenAI API | WBS generation from scope text |
| Embedding model | all-MiniLM-L6-v2 | Semantic task-member matching |
| Duration model | XGBoost Regressor | Task effort estimation |
| Fallback duration | Heuristic rules | Used when trained model is unavailable |
| Working hours/day | 8 hours | Conversion from estimated hours to working days |
| Calendar rule | Monday-Friday | Weekend days are skipped |
| Graph library | NetworkX | Critical path and topological ordering |
| Default database URL | sqlite+aiosqlite:///./scaffoldpm.db | Development database location |
| Allowed frontend origin | http://localhost:3000 | CORS origin for future Next.js frontend |

This completes the system design specification for ScaffoldPM. The modular FastAPI backend, document extraction workflow, LLM-based WBS generation, semantic task matching, duration prediction, dependency-aware scheduling, critical path analysis, and relational persistence design provide a clear blueprint for implementation and future frontend integration.

# REFERENCES

[1] Project Management Institute, A Guide to the Project Management Body of Knowledge (PMBOK Guide), 7th ed. Project Management Institute, 2021.

[2] Project Management Institute, Practice Standard for Work Breakdown Structures, 3rd ed. Project Management Institute, 2019.

[3] R. T. Hans, "Work Breakdown Structure: A Tool for Software Project Scope Verification," arXiv:1308.2876, 2013.

[4] J. E. Kelley Jr. and M. R. Walker, "Critical-path planning and scheduling," in Proc. Eastern Joint IRE-AIEE-ACM Computer Conference, 1959.

[5] N. Reimers and I. Gurevych, "Sentence-BERT: Sentence embeddings using Siamese BERT-networks," arXiv:1908.10084, 2019.

[6] T. Chen and C. Guestrin, "XGBoost: A scalable tree boosting system," in Proc. 22nd ACM SIGKDD International Conference on Knowledge Discovery and Data Mining, 2016, pp. 785-794.

[7] B. W. Boehm, Software Engineering Economics. Prentice-Hall, 1981.

[8] A. Trendowicz, J. Munch, and R. Jeffery, "State of the practice in software effort estimation: A survey and literature review," arXiv:1401.5878, 2014.

[9] Y. Mahmood, N. Kama, A. Azmi, A. S. Khan, and M. Ali, "Software effort estimation accuracy prediction of machine learning techniques: A systematic performance evaluation," arXiv:2101.10658, 2021.

[10] FastAPI, "FastAPI documentation." https://fastapi.tiangolo.com/

[11] Pydantic, "Pydantic documentation: Models." https://docs.pydantic.dev/latest/concepts/models/

[12] SQLAlchemy, "SQLAlchemy 2.0 documentation: Asynchronous I/O." https://docs.sqlalchemy.org/en/20/orm/extensions/asyncio.html

[13] SQLite, "About SQLite." https://www.sqlite.org/about.html

[14] LangChain, "LangChain overview." https://docs.langchain.com/oss/python/langchain/overview

[15] OpenAI, "Text generation guide." https://platform.openai.com/docs/guides/text

[16] OpenAI, "Structured model outputs." https://platform.openai.com/docs/guides/structured-outputs

[17] Sentence Transformers, "SentenceTransformers documentation." https://www.sbert.net/

[18] XGBoost Developers, "XGBoost documentation." https://xgboost.readthedocs.io/

[19] NetworkX Developers, "topological_sort - NetworkX documentation." https://networkx.org/documentation/stable/reference/algorithms/generated/networkx.algorithms.dag.topological_sort.html